## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
School Management System ¦ Capstone Group Project
| Organizations | CTU
| Project | School Management System
| Product Owner | Miguel
| Scrum Master | Brian Keener
| Development Team | Nadia, Miguel, Robert, Brian
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
E1 | Manage Student Records | Add/Edit/Delete student profiles | Admin can manage student records | High | 1 | Input validation, role-based access
E2 | Academic Performance Management | Enter and view student grades | Teachers can submit grades and students can view them | High | 1 | Grade validation, access restrictions
E3 | Manage Teacher Profiles | Add/Edit teacher details | Admin can update teacher info | Medium | 1 | Secure profile management
E4 | Assign Teachers to Classrooms | Map teachers to subjects/classrooms | Admin can assign teachers to specific classes | High | 1 | Verify role permissions
E5 | Allocate Classrooms | Assign class IDs and manage capacity | Admin can assign students/teachers to rooms | Medium | 1 | Enforce 20-student limit, validate assignments
E6 | Authentication and Roles | Secure login and role-based dashboards | Users log in and access correct dashboard | High | 2 | Use JWT/HTTPS, rate-limit, audit logs
E7 | Teacher Dashboard | View assigned classes, enter grades | Teachers can see class list and submit results | High | 2 | Restrict cross-class access
E8 | Student Dashboard | View personal info and grades | Students can access profile and grades | High | 2 | Read-only access, encrypted storage
E9 | Class Capacity Rule | Limit classes to 20 students | System prevents adding more than 20 students | Medium | 2 | Backend constraint enforcement
E10 | View Student Performance | Teachers view student academic history | Teachers see correct and updated grades | Medium | 2 | Audit access, permissions check
E11 | Admin Dashboard | View all teachers/students with full creation, read, update and deletion access | Admins designed user interface with full access | High | 2 | Logs of all actions to cloud-db

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | School Management System
|  | Sprint # |  | 1
|  | Start date |  | 2025-06-10
Total Team Members
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23
1 | E1 | Add/Edit/Delete student profiles | Input validation, role-based access | 2 | 2025-06-10: 2
2 | E2 | Enter and view student grades | Grade validation, access restrictions | 8 | 2025-06-10: 4; 2025-06-13: 4
3 | E3 | Add/Edit teacher details | Secure profile management | 6 | 2025-06-10: 3; 2025-06-12: 1; 2025-06-15: 2
4 | E4 | Map teachers to subjects/classrooms | Verify role permissions | 6 | 2025-06-11: 1; 2025-06-14: 5
5 | E5 | Assign class IDs and manage capacity | Enforce 20-student limit, validate assignments | 7 | 2025-06-10: 4; 2025-06-13: 1; 2025-06-15: 2
|  | Remaining units (actual) |  | 0 | -13 | -14 | -15 | -20 | -25 | -29 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 29 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | School Management System
|  | Sprint # |  | 2
|  | Start date |  | 2025-06-24
Total Team Members
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07
6 | E6 | Authentication and Roles | Use JWT/HTTPS, rate-limit, audit logs | 10
7 | E7 | Teacher Dashboard | Restrict cross-class access | 10
8 | E8 | Student Dashboard | Read-only access, encrypted storage | 10
9 | E9 | Class Capacity Rule | Backend constraint enforcement | 10
10 | E10 | View Student Performance | Audit access, permissions check | 10
10 | E11 | Admin Dashboard | Admins designed user interface with full access | 10
|  | Remaining units (actual) |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 60 | [5 empty] | 0 | 0
[9 empty] | 10 | 0 | [5 empty] | 10 | 0